## Sheet1
Survival of the Fittest - Bug Tracking
Number | Date Found | Finder | Type | Priority | Who will deal with it? | Summary | Date Fixed | Low | Med | High | Fixed
1 | 2016-04-08 | Charles | Code - Asthetics | Med | Charles | Bullets fire from the center of the sprite, instead of from the edge and where guns would be
2 | 2016-04-09 | Charles | Code - Asthetics | Med | Charles | Bullets continue to fire left for a short time after the player has turned to the right | 2016-04-09
3 | 2016-04-15 | Charles | Code - Function | High | Charles | Camera moves with primary character, but that includes movement on the y axis, revealing edges of the map | 2016-04-18
4 | 2016-04-15 | Charles | Code - Function | High | Charles | Players hitting walls, while holding left or right, refuse to fall via gravity, until the direction is not being held | 2016-04-20
5 | 2016-04-20 | Charles | Code - Function | High | Charles | Player doesn't repsawn at designated checkpoint after death | 2016-04-21
6 | 2016-04-21 | Charles | Code - Function | High | Charles | Game fails to recognize the first player past the finish line | 2016-04-21
7 | 2016-04-22 | Charles | Code - Function | High | Charles | Switching to gamepad controls allows the player to jump infinitely | 2016-04-22
8 | 2016-04-22 | Charles | Code - Function | High | Charles | Players 1 and 2 move in unison | 2016-04-22
9 | 2016-04-22 | Charles | Code - Function | High | Charles | Player 2 on respawn doesn't die from gun fire | 2016-04-22
10 | 2016-04-22 | Charles | Code - Function | High | Charles | Only players 1 and 2 respawn after death, even with 4 players | 2016-04-22
11 | 2016-04-22 | Charles | Code - Function | High | Charles | On respawn, player 4 respawns twice if all 4 players die | 2016-04-22
12 | 2016-04-22 | Charles | Code - Function | High | Charles | Player 3 respawned when still alive at respawn | 2016-04-22
13 | 2016-04-22 | Charles | Code - Function | High | Charles | If Player 1 is the only one alive, the game fully crashes | 2016-04-22
14 | 2016-04-24 | Charles | Code - Function | High | Charles | Menu only displays 1 button instad of 3